DRAFT PROGRAMME OF WORK (2016-2018)

TO SUPPORT THE IMPLEMENTATION OF THE MEMORANDUM OF UNDERSTANDING ON THE CONSERVATION OF MIGRATORY SHARKS

| No. | Activities | Mandate | Priority ranking | Time frame | Responsible entity | Funding |
| --- | --- | --- | --- | --- | --- | --- |
| Species Conservation |  |  |  |  |  |  |
|  | Establish and convene a Conservation Working Group (CWG) under the Advisory Committee in accordance with the Terms of Reference as defined in CMS/Sharks/MOS2/ Outcome # | AC1 | high | 2016-2018 | AC SEC CWG Cooperating Partners Consultant | Budget + Fundraising |
|  | Convene a CWG workshop | CP 1.1 CP 1.7 | high | 2017 | AC CWG SEC Consultant | Budget + Fundraising |
|  | Provide recommendations to the AC and produce reports on activities to AC meetings | AC1 | high | As required | CWG | Budget |
|  | Facilitate communication and support Signatories in the identification of regional and local research projects - Consult regularly with Focal Points - Based on the outcomes of the Species-specific Action Plans (Activity 1), communicate to focal points relevant activities to be implemented in their region - Seek funding opportunities (refer to activity 58) | CP 1.2 SEC ToR | core | 2016-2018 | SEC | Budget |
|  | When instructed by Signatories to do so, identify or develop suitable conservation projects, partners for implementation and manage Funding Agreements | CP 1.2 CP 1.3 SEC ToR | core | 2016-2018 | SEC | Fundraising |
| Bycatch |  |  |  |  |  |  |
|  | Liaise with CMS Bycatch Working Group and participate in CMS bycatch workshops | SEC ToR | core | 2016-2018 | AC CWG SEC | Budget |
| Fisheries Management and data collection |  |  |  |  |  |  |
|  | Expand and encourage fisheries-independent research (e.g. historic data on commercially exploited species) to provide additional data for use in the fishery stock assessments and to inform relevant RFMOs | CP 2.6 CP 3.2 | medium | 2016-2018 | SIG | Fundraising |
|  | Promote research focussing on the identification of species-selective fishing gear and bycatch mitigation measures | CP 4.5 | medium | 2016-2018 | SIG | Fundraising |
|  | Fund and support national and international training courses in : - data collection - shark identification - handling and safe release protocols | CP 1.2 | high | 2016-2018 | SIG SEC | Fundraising |
|  | Encourage all Range States to join CMS and become Signatories to the MOU, and to comply with the decisions and recommendations. | CP 16.2 | high | 2016-2018 | SIG SEC Cooperating Partners | Budget |
|  | Liaise with CITES, IUCN, TRAFFIC FAO and other relevant UN bodies to facilitate the implementation of CMS Appendix II and CITES Appendix II listings and raise awareness through regional capacity-building workshops on sustainable harvest and trade, particularly in relation to: - NDF - Traceability - Species identification | CP 7.2 CP 14.3 | medium | 2016-2018 | SEC | Fundraising |
|  | Improve monitoring and implementation in marine protected areas (MPAs), improve enforcement | CP 14.5 | medium | 2016-2018 | SIG | Fundraising |
| Cooperation and Partnerships |  |  |  |  |  |  |
|  | Cooperate with the CMS Family on matters related to shark conservation - Contribute to the implementation of CMS Res. 11.20, Resolutions on bycatch (CMS wide bycatch workshop) - Contribute to the preparation of CMS COP12 and other relevant meetings of CMS (ScC, StC) | SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Contribute to the implementation of the CMS CITES Joint Work Programme 2015-2020 regarding sharks and rays - Activity B17: Optimize the effectiveness of actions taken by Parties to both CMS and CITES concerning sharks and rays, strengthening synergies with FAO, RSCs, RFBs and other relevant bodies - Activity B18: Cooperate on capacity building regarding the implementation of regulations of both Conventions related to sharks and rays | CP 14.3 SEC ToR | core | 2016-2018 | SEC | Budget + Fundraising |
|  | Strengthen synergies and collaborate in conjunction with CITES and FAO to support regional programmes as well as collaboration between Range States - Organize regular meetings (and teleconference calls ) - Share best practice - Coordinate conservation activities - Share knowledge and expertise | CP 13.1 CP 14.3 SEC ToR | core | 2016-2018 | AC SEC | Budget |
|  | Establish partnerships and strengthen collaboration with relevant international organizations and agreements dealing with shark conservation and management | CP 13.1 CP 14.3 SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Promote conservation efforts and cooperation between all stakeholders in Range States | CP 13.1 SEC ToR | core | 2016-2018 | SEC | Budget |
|  | IUCN Red List Assessments - Liaise with the IUCN Shark SSG to coordinate actions implementing the objectives of the Conservation Plan and the species-specific action plans - Participate in assessment workshops to provide recommendations and organize side events | CP 13.1 | high | 2016-2018 | AC CWG SEC | Budget |
| Management of the Secretariat |  |  |  |  |  |  |
|  | Manage and implement the budget for the MOU | SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Prepare annual budget implementation reports for the information of the Signatories and project reports to donors | SEC ToR | core | yearly | SEC | Budget |
|  | Undertake Fundraising activities | SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Maintain and update the Sharks MOU website as needed | SEC ToR | core | 2016-2018 | SEC Consultant | Budget |
|  | Publish articles and press releases relevant to shark conservation and management supported by the CMS Joint Communications Team | SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Produce fact sheets about relevant shark conservation and where appropriate measures to achieve sustainable fisheries, for relevant topics and species - Bycatch - Overfishing - Species Action Plans | SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Use Social Media to increase the visibility of the MOU globally supported by the CMS Joint Communications Team | SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Prepare publications using studies (e.g. domestic legislation, species priorities) | SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Expand the Sharks MOU communication and awareness-raising activities, in particular to: · Develop a distinct visual identity for the Sharks MOU; · Develop a distinct website for the sharks MOU; · Develop a distinct email address; · Outreach relevant bodies and organizations, in consultation with Signatories; · Outreach, in consultation with Signatories, Non-Signatory Range-States and in particular those that display significant catches, trade and consumption of sharks. Where feasible, align communication with the Communication Strategy for Migratory Species (in preparation) Where feasible, expand the Sharks MOU communication and awareness-raising activities in alignment with the Communication Strategy for Migratory Species (in preparation) | SEC ToR | core | 2016-2018 | SEC | Fundraising |
|  | Compile information, review data, liaise with stakeholders and provide information to Signatories on the implementation and functioning of the MOU | SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Facilitate and encourage regular information exchange and cooperative activities between - the shark research,conservation and sustainable fisheries communities - stakeholders in all Range States - Focal Points - Advisory Committee | SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Represent the MOU at meetings of other intergovernmental agreements (e.g. CITES, IUCN, FAO), as appropriate to facilitate the achievement of the objectives of the MOU | SEC ToR | core | 2016-2018 | SEC | Budget + Fundraising |
|  | Update and maintain the contact database | SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Prepare reports of the Secretariat activities for AC and MOS meetings | SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Recruit and manage the staff and interns of the Secretariat | SEC ToR | core | 2016-2018 | SEC | Budget |
| Support for Meetings (MOS, AC and WG) |  |  |  |  |  |  |
|  | Undertake meeting arrangements for the 3rd Meeting of the Signatories (MOS3), including the identification of a venue, liaison with host government and organization of contracts | SEC ToR | core | End 2018 | SEC | Budget |
|  | Undertake meeting arrangements for the 2nd Meeting of the Advisory Committee (AC2), including the identification of a venue and organization of contracts | SEC ToR | core | Mid 2017 | SEC | Budget |
|  | Undertake meeting arrangements for the 3rd Meeting of the Advisory Committee (AC3), including the identification of a venue and organization of contracts | SEC ToR | core | Mid 2018 | SEC | Budget |
|  | Undertake meeting arrangements for the Working Group Meetings, including the identification of a venue and organization of contracts | SEC ToR | core | 2016 and 2017 | SEC | Budget + Fundraising |
|  | Coordinate, draft and prepare meeting documents, including posting of documents | SEC ToR | core | 2016-2018 | SEC Consultant | Budget |
|  | Coordinate and prepare translations into 3 languages (English, French and Spanish) | SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Support and arrange attendance and travel of sponsored delegates and experts | SEC ToR | core | 2016-2018 | SEC | Budget + Fundraising |
|  | Organize and prepare media and press work in collaboration with the Joint Communication Team of CMS | SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Prepare meeting reports and distribute to Signatories | SEC ToR | core | 2016-2018 | SEC | Budget |
| Support of the Advisory Committee |  |  |  |  |  |  |
|  | Assist the Chair of the Advisory Committee as required to facilitate the work of the Committee | SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Assist the Advisory Committee with the preparation of meeting documents | SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Assist the convenor and chair of the Conservation Working Group, as required to facilitate the work | SEC ToR | core | 2016-2018 | SEC Consultants | Budget |
|  | Develop and maintain the list of experts relevant to the Sharks MOU | CP 2.5 | core | 2016-2018 | SEC | Budget |
| Implementation of the MOU |  |  |  |  |  |  |
|  | Promote and coordinate activities of the Programme of Work and Conservation Plan | SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Conduct a survey on domestic legislation to address implementation gaps, inform Signatories and monitor the implementation of the Conservation Plan | CP 7.1 SEC ToR | core | 2016-2018 | SEC | Budget |
|  | Liaise with non-Signatory Range States to provide them with the necessary information to join the MOU and facilitate the accession | SEC ToR | core | 2016-2018 | SEC Cooperating partners | Budget |
|  | Undertake outreach activities on the following priority regions: South-East Asia, South America and Caribbean and West Africa | SEC ToR | core | 2016-2018 | SEC Cooperating partners | Fundraising |
|  | Use other CMS meetings and workshops to promote the accession to the MOU | SEC ToR | core | 2016-2018 | SEC CMS | Budget |
| Capacity Building |  |  |  |  |  |  |
|  | Identify and review gaps in capacity and training needs of Signatories and compile or develop tailored training materials | CP 1.1 SEC TOR | high | 2016-2018 | AC SEC Cooperating Partners | Fundraising |
|  | Assist Signatories with the implementation of the Conservation Plan. | CP 6.2 SEC ToR | high | As requested by Signatories | AC SEC Cooperating Partners | Fundraising |
|  | Contribute to joint capacity-building workshops with CMS and cooperating partners in Africa, Asia, Oceania, South & Central America and the Caribbean, as requested by the regions | SEC ToR | core | 2016-2018 | SIG AC SEC Cooperating Partners | Fundraising |
|  | Develop a communication and awareness raising strategy for CMS Sharks MOU -listed species | CP 1.6 CP 5.2 CP 6.3 | high | 2016-2018 | SIG SEC Cooperating Partners | Budget |
|  | Develop a Massive Open Online Course (MOOC) on the Conservation and Management of Sharks and their habitats Cooperate with relevant scientific bodies (universities, scientists, international institutions) | CP 12 | medium | 2017 | SEC Cooperating Partners | Fundraising |
|  | Translation of “Sharks of the Arabian Seas”- Identification Guide to other languages of the Indian Ocean Region (e.g. Farsi, Hindi, Urdu) and other identification guides as required | CP 12 CP13 | medium | 2016-2017 | SEC | Fundraising |
| Fundraising / Mobilization of resources |  |  |  |  |  |  |
|  | Identify existing and new opportunities for financial resources to support the long-term implementation of the Conservation Plan and the PoW. Expand and enhance fundraising activities: - Raise funds and voluntary annual contributions from Signatories - Raise funds for joint projects with partners and potential partners - Explore possibilities of alternative funds (e.g. private sector) - Support funding applications and opportunities for Signatories - with letters of endorsement / support | SEC ToR | core | 2016-2018 | SIG SEC | Budget |

Conservation Plan (CP) and the Terms of Reference of the Advisory Committee and the Secretariat (SEC ToR)

Core Secretariat activities and suggested priorities (High, Medium)

Year(s) during which activity should be implemented

Signatories (SIG), Advisory Committee (AC), Secretariat (SEC), Conservation Working Group (CWS), Consultants, Cooperating Partners

Fundraising Scenario 1 or 2 from the proposed budget 2016-2018 CMS/Sharks/MOS2/Doc.10.1 and activities that require special fundraising