(from CMS/Sharks/MOS3/Doc.16.1/Annex 1)

|  | ## MEMORANDUM OF UNDERSTANDING ON THE CONSERVATION OF MIGRATORY SHARKS | CMS/Sharks/MOS3/CRP11 13 December 2018 |
| --- | --- | --- |

PROGRAMME OF WORK (2019-2021)

TO SUPPORT THE IMPLEMENTATION OF THE MEMORANDUM OF UNDERSTANDING ON THE CONSERVATION OF MIGRATORY SHARKS

PROGRAMME OF WORK (2019-2021)

TO SUPPORT THE IMPLEMENTATION OF THE MEMORANDUM OF UNDERSTANDING ON THE CONSERVATION OF MIGRATORY SHARKS

| No. | Activities | Mandate | Priority ranking | Time frame | Responsible entity | Funding | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Species Conservation/Habitat Conservation |  |  |  |  |  |  |  |
| 2. 1. | Provide support to the implementation of CMS Concerted Action Plans as adopted in CMS/Sharks/Outcome 3.x. The Secretariat, with support from the AC as required, is requested to: - assist the government of the Philippines with the organization of a regional workshop on the conservation of whale sharks in Southeast Asia. - [assist the Principality of Monaco with the organization of regional workshops on the conservation of the Angelshark, in particular in the Mediterranean region.] | Outcome 3.x | high | 2019-2021 | SIG SEC CooP AC | Fundraising | New activity: to be further developed during MOS3 (agenda item 15) |
| 3 2 | Further develop and prioritize suggested areas of action as contained in Outcome 3.x (10.1) with options by taxa, region, and other relevant factors. . | MOS3 | high | 2019-2021 | AC | Budget | New activity |
| 4 3 | Facilitate communication and support Signatories with the identification of regional and local projects. | CP 1.2 SEC TOR | core | 2019-2021 ongoing activity | SEC AC | Budget | Carried over from POW 16-18 (activity 4) |
| 5 4 | When instructed by Signatories to do so, identify suitable partners for implementation and manage Funding Agreements for conservation projects. | CP 1.2 CP 1.3 SEC TOR | core | 2019-2021 | SEC AC | Fundraising | Carried over from POW 16-18 (activity 5) |
| Fisheries Management and data collection (incl. bycatch) |  |  |  |  |  |  |  |
| 6 5 | Encourage collation of those data that are relevant to RFMOs and stock assessments (e.g. fisheries-independent data, historical and traditional data) and promote their dissemination. | CP 2.6 CP 3.2 | medium | 2019-2021 | SIG | Fundraising | Carried over from POW 16-18 (activity 7) |
| 7 6 | Promote research focussing on the identification of species-selective fishing gear and bycatch mitigation measures, with emphasis on those Annex 1 listed species which are known to experience high post release mortality (e.g. sawfish, thresher sharks, hammerhead sharks). | CP 4.5 | medium | 2019-2021 | SIG CooP | Fundraising | Carried over from POW 16-18 (activity 8) |
| 7 | Set up a repository for relevant information to assist managers, including species identification, bycatch mitigation and safe handling, discard survival, and other relevant fisheries management information. Encourage Signatories to provide such information to the Secretariat. | MOS3 | medium | 2019-2021 | AC SEC SIG | Budget |  |
| 8. | Finalize existing species factsheets and draft species factsheets for species newly listed in Annex 1 of the MOU. | MOS3 | high | 2019 | AC | Budget | New activity |
| 9 | Improve, where appropriate, monitoring, implementation and enforcement of relevant spatial management measures. | CP 14.5 | medium | 2019-2021 | SIG | Fundraising | Carried over from POW 16-18 (activity 12) |
| Capacity Building |  |  |  |  |  |  |  |
| 10 | Implement the Capacity-building Programme for the MOU as adopted in CMS/Sharks/Outcome 3.x to assist Signatories with the implementation of the Conservation Plan. | CP 1.1 CP 6.2 SEC TOR MOS3 | high | 2019-2021 | SIG AC SEC CooP | Fundraising |  |
| Cooperation and Partnerships |  |  |  |  |  |  |  |
| 11 | Cooperate with the CMS Family on matters related to shark conservation: - Contribute to the implementation of - CMS Res. 12.20 on “Management of Marine Debris”; - CMS Res. 12.22 on “Bycatch”; - CMS Res. 12.23 on “Sustainable Tourism and Migratory Species”; - CMS Res. 12.24 on “Promoting Marine Protected Area Networks in the ASEAN Region”; - Contribute to the preparation of CMS COP13 and other relevant meetings of CMS (ScC, StC); - Provide comments on proposals for the inclusion of shark and ray species in the Appendices of CMS to the CMS Scientific Council and Conference of the Parties. | SEC TOR MOS3 | core | 2019-2021 | SEC AC | Budget | Carried over from POW 16-18 (activity 13); relevant CMS Resolutions added, and additional activity of the AC included |
| 12 | Strengthen synergies and collaborate with CITES and FAO: - Contribute to the implementation of the CMS-CITES Joint Work Programme 2015-2020 regarding sharks and rays; - Include activities on sharks and rays in a new CMS-CITES Joint Work Programme with the CITES Secretariat in consultation with Signatories; - Organize regular meetings (and teleconferences); - Share best practice; - Coordinate conservation activities; - Share knowledge and expertise. | SEC TOR | high | 2019-2021 | AC SEC | Budget + Fundraising | Carried over from POW 16-18 (activity 14 and 15); and updated |
| 13 | [Implement the process and activities to engage with Regional Fisheries Management Organizations as agreed in CMS/Sharks/Outcome 3.x. (11.1)]. | MOS3 | tbd | tbd | tbd | tbd | New activity: to be further developed during MOS3 (agenda item 11) |
| 14 | Establish partnerships and strengthen collaboration with other relevant international organizations and agreements dealing with shark science, conservation and management. | CP 13.1 CP 14.3 SEC TOR | core | 2019-2021 | SEC | Budget | Carried over from POW16-18 (activity 16) |
| 15 | Encourage all Range States to join CMS and become Signatories to the MOU. | CP 16.2 | high | 2019-2021 | SIG SEC CooP | Budget | Carried over from POW16-18 (activity 10), moved from Fisheries management section. |
| 16 | - Liaise with the IUCN Shark SSG and - participate in assessment workshops, where relevant. | CP 13.1 | high | 2019-2021 | AC CWG SEC | Budget | Carried over from POW16-18 (activity 18) |
| Management of the Secretariat |  |  |  |  |  |  |  |
| 17 | Manage and implement the budget for the MOU. | SEC TOR | core | 2019-2021 | SEC | Budget | Carried over from POW16-18 (activity 19) |
| 18 | Prepare annual budget implementation reports for the information of the Signatories and project reports to donors. | SEC TOR | core | yearly | SEC | Budget | Carried over from POW16-18 (activity 20) |
| 19 | Inform and raise awareness about the Sharks MOU in accordance with the “Communication and Awareness raising Strategy of the Sharks MOU. | SEC TOR | core | 2019-2021 | SEC Consultant | Budget | Carried over from POW16-18 (activity 22, 23, 24, 25) |
| 20 | Prepare publications as required (e.g. domestic legislation, species priorities). | SEC TOR | core | 2019-2021 | SEC | Budget | Carried over from POW16-18 (activity 26) |
| 21 | Compile information, review data, liaise with stakeholders and provide information to Signatories on the implementation and functioning of the MOU. | SEC TOR | Core | 2019-2021 | SEC | Budget | Carried over from POW16-18 (activity 28) |
| 22 | Facilitate and encourage regular information exchange and cooperative activities between: - the shark research and conservation community; - stakeholders in all Range States; - Focal Points; - Advisory Committee. | SEC TOR | core | 2019-2021 | SEC | Budget | Carried over from POW16-18 (activity 29) |
| 23 | Represent the MOU at meetings of other intergovernmental agreements (e.g. CITES, IUCN, FAO), as appropriate to facilitate the achievement of the objectives of the MOU. | SEC TOR | Core | 2019-2021 | SEC | Budget + Fundraising | Carried over from POW16-18 (activity 30) |
| 24 | Prepare reports of the Secretariat activities for AC and MOS meetings. | SEC TOR | core | 2019-2021 | SEC | Budget | Carried over from POW16-18 (activity 32) |
| 25 | Recruit and manage the staff and interns of the Secretariat. | SEC TOR | core | 2019-2021 | SEC | Budget | Carried over from POW16-18 (activity 33) |
| Support for Meetings (MOS, AC and WG) |  |  |  |  |  |  |  |
| 26 | Undertake meeting arrangements for the 4th Meeting of the Signatories (MOS4): - Identify a venue and liaise with the host government; - Develop the draft agenda in consultation with Signatories; - Coordinate, draft and prepare meeting documents, including posting of documents; - Coordinate and prepare translations into 3 languages (English, French and Spanish); - Support and arrange attendance and travel of sponsored delegates and experts; - Handle contracts with interpreters, report writers and other staff, as required; - Organize and prepare media and press work in collaboration with the Joint Communication Team of CMS; - Prepare and publish a report of the meeting. | SEC TOR | core | 2021 | SEC | Budget | Carried over from POW16-18 (activities 34, 38, 39, 40, 41, 42); updated and rearranged to include all tasks related to the activity |
| 27 | Undertake meeting arrangements for the 3rd Meeting of the Advisory Committee (AC3): - Identify a venue and liaise with the host government; - Develop the draft agenda in consultation with the AC; - Coordinate, draft and prepare meeting documents, including posting of documents; - Support and arrange attendance and travel of sponsored participants and experts; - Handle contracts with interpreters, report writers and other staff, as required; - Organize and prepare media and press work in collaboration with the Joint Communication Team of CMS; - Prepare and publish a report of the meeting. | SEC TOR | core | 2019 | SEC | Budget | Carried over from POW16-18 (activities 35, 38, 39, 40, 41, 42); updated and rearranged to include all tasks related to the activity |
| 28 | Undertake meeting arrangements for the 4th Meeting of the Advisory Committee (AC4): - Identify a venue and liaise with the host government; - Develop the draft agenda in consultation with the AC; - Coordinate, draft and prepare meeting documents, including posting of documents; - Support and arrange attendance and travel of sponsored participants and experts; - Handle contracts with interpreters, report writers and other staff, as required; - Organize and prepare media and press work in collaboration with the Joint Communication Team of CMS; - Prepare and publish a report of the meeting. | SEC TOR | core | 2020 | SEC | Budget | Carried over from POW16-18 (activities 36, 38, 39, 40, 41, 42); updated and rearranged to include all tasks related to the activity |
| Support of the Advisory Committee |  |  |  |  |  |  |  |
| 29 | Assist the Chair of the AC as required to facilitate the work of the Committee and the preparation of meeting documents. | SEC TOR | core | 2019-2021 | SEC | Budget | Carried over from POW16-18 (activity 43 and 44) |
| Implementation of the MOU |  |  |  |  |  |  |  |
| 30 | Review the implementation of the Conservation Plan and the Programme of Work and present a report to MOS4. The report should be based on an analysis of National Reports from Signatories, Reports from Cooperating Partners, activities undertaken by the AC and the Secretariat. | SEC TOR | core | 2021 | SEC | Budget | New activity |
| 31 |  |  |  |  |  |  |  |
| 32 31 | Liaise with non-Signatory Range States to provide them with the necessary information to join the MOU and facilitate accession. | SEC TOR | core | 2019-2021 | SEC CooP SIG | Budget | Carried over from POW16-18 (activity 49) |
| Fundraising / Mobilization of resources |  |  |  |  |  |  |  |
| 33 32 | Identify existing and new opportunities for financial resources to support the long-term implementation of the Conservation Plan and the POW. Expand and enhance fundraising activities: - Develop a fundraising strategy for the MOU - Raise funds and voluntary annual contributions from Signatories; - Raise funds for joint projects with partners and potential partners; - Explore possibilities of alternative funds (e.g. private sector); - Support funding applications and opportunities for Signatories and Cooperating Partners. | SEC TOR | core | 2019-2021 | SIG SEC CooP | Fundraising | Carried over from POW16-18 (activity 58) |

Conservation Plan (CP), Terms of Reference of the Advisory Committee (AC TOR), Terms of Reference of the Secretariat (SEC TOR)

Core Secretariat activities and suggested priorities (High, Medium)

Year(s) during which activity should be implemented

Signatories (SIG), Advisory Committee (AC), Secretariat (SEC), Conservation Working Group (CWS), Consultants, Cooperating Partners (CooP)

13th Conference of the Parties to the Convention on the Conservation of Migratory species of Wild Animals

Scientific Council

Standing Committee

CITES – Convention on International Trade in Endangered Species of Wild Fauna and Flora

FAO – Food and Agriculture Organization of the United Nations